## Funnel
Client | Service | Action Item | Person In Charge | Person Email | Due Date | Status | Potential Revenue | Aging (Days) | Notes | Created By | Created At | Updated At
JMTI | Training | Raise new pr for JMTI Corporate shirt- 34 pieces | Solehin | Solehin | 2026-08-24 | In Progress | 0 | 0 |  | qusyairi.zolkefle@gmail.com | 19/08/2026, 10:07:47 am | 19/08/2026, 10:07:47 am
Mimos Holding | Training Certificate completion | Training certificate completion | solehin | Solehin | 2026-08-28 | In Progress | 0 | 0 |  | qusyairi.zolkefle@gmail.com | 19/08/2026, 10:06:08 am | 19/08/2026, 10:06:08 am
Proposal TTT AI (Naio) | Training | Submit Proposal by 4 September | Omar | Omar | 2026-09-04 | In Progress | 0 | 2 |  | qusyairi.zolkefle@gmail.com | 17/08/2026, 8:36:23 am | 19/08/2026, 9:53:07 am
NDA TTT AI (Naio) | Training | submit NDA | Sarah | Sarah | 2026-08-24 | In Progress | 0 | 2 |  | qusyairi.zolkefle@gmail.com | 17/08/2026, 8:25:52 am | 17/08/2026, 4:08:52 pm
MARA | Training | Hardcopy proposal submitted to MARA | Adila/Fuziah | Adila/Fuziah | 2026-08-13 | Done | 300000 | 6 |  | qusyairi.zolkefle@gmail.com | 13/08/2026, 5:17:58 pm | 13/08/2026, 5:17:58 pm
SST JMTI | Governance | need to give feedback to JMTI in 7 days | yusuf | yusuf | 2026-08-19 | In Progress | 0 | 6 | sarah has email to request for extension 2 weeks | qusyairi.zolkefle@gmail.com | 13/08/2026, 10:26:48 am | 18/08/2026, 4:26:42 pm
Mara | Training | Semiconductor | fuzi | fuzi | 2026-08-13 | Done | 0 | 6 | revise price . | qusyairi.zolkefle@gmail.com | 13/08/2026, 10:12:06 am | 13/08/2026, 5:18:38 pm
To Find GTM Staff under Farrah | Coordination | Find one Staff under GTM for coordination | farrah | farrah | 2026-08-28 | In Progress | 0 | 6 |  | qusyairi.zolkefle@gmail.com | 13/08/2026, 10:01:23 am | 13/08/2026, 10:01:23 am
Register MASB under Mimos Berhad | Registration | To register MASB under Mimos Berhad | yusuf | yusuf | 2026-08-14 | Done | 0 | 7 | registration completed | qusyairi.zolkefle@gmail.com | 12/08/2026, 10:24:07 am | 18/08/2026, 2:33:58 pm
update on courtesy Visit | Meeting | 3 company baru bagi feedback untuk surat kunjung hormat. 1 courtesy visit 17/8/2026 confirm with dr nizar schedule. | firzana | firzana | 2026-08-17 | In Progress | 0 | 7 | [18/8/2026] 5 company has provide the feedback. only ITBM completed the courtesy visit yesterday | qusyairi.zolkefle@gmail.com | 12/08/2026, 10:22:44 am | 18/08/2026, 9:46:49 am
MAMC TOR Guideline | Guideline | come out with guideline | abu said | abu said | 2026-08-13 | Done | 0 | 7 |  | qusyairi.zolkefle@gmail.com | 12/08/2026, 10:15:27 am | 19/08/2026, 9:29:00 am
PUNB | training | Ai Training. Proposal for develop platform (vibe coding). 3 Days training | Adilah |  | 2026-08-14 | In Progress | 31500 | 7 | proposal pending from Suhairi(cost outline) | qusyairi.zolkefle@gmail.com | 12/08/2026, 9:52:09 am | 12/08/2026, 9:52:09 am
Mindef HAT | Training | Ai Training. 4 Different group Training for HAT staff | Adilah | Adilah | 2026-09-15 | In Progress | 70000 | 7 | [12/08/2026] proposal in progress | qusyairi.zolkefle@gmail.com | 12/08/2026, 9:39:26 am | 12/08/2026, 11:08:55 am
Budiman Dinamik | Consulting | buat nda teaming agreement share proposal semiconductor poster yellow belt september poster train the trainer nov | Farrah | Farrah | 2026-08-12 | In Progress | 0 | 8 |  | qusyairi.zolkefle@gmail.com | 11/08/2026, 4:32:44 pm | 11/08/2026, 4:32:44 pm
Mockup Internal Training | Training | Mockup Training | Dr Nizar | Dr Nizar | 2026-08-25 | In Progress | 0 | 12 |  | qusyairi.zolkefle@gmail.com | 07/08/2026, 6:22:47 pm | 07/08/2026, 6:22:47 pm
PMP Refresher internal training | Training | Half Day Training | Dr nizar | Dr Nizar | 2026-08-24 | In Progress | 0 | 12 |  | qusyairi.zolkefle@gmail.com | 07/08/2026, 6:21:38 pm | 10/08/2026, 2:28:54 pm
OA MIMOS | Consulting | knowledge Sharing booking System for training room to all OA in MIMOS | Abu Sa'id | Abu Said | 2026-08-05 | Done | 0 | 14 |  | qusyairi.zolkefle@gmail.com | 05/08/2026, 10:47:57 am | 18/08/2026, 5:19:41 pm
AI-CoE in ARMC | PO and INVOICE | To compile quotation PO and INVOICE(Hardcopy) | Yusof | yusof | 2026-08-05 | In Progress | 0 | 14 | Team Kene masukkan semua invoice po and do dalam folder. pending from MA Team to provide | qusyairi.zolkefle@gmail.com | 05/08/2026, 10:23:04 am | 12/08/2026, 10:20:16 am
Zamri | Consulting | To follow up with Zamri on DOA and invoice | Solehin | Solehin | 2026-08-07 | Done | 0 | 14 | 6/8/2026 request in process [18/8/2026] we have received the invoice from Finance . | qusyairi.zolkefle@gmail.com | 05/08/2026, 10:20:55 am | 18/08/2026, 9:40:16 am
AI-CoE in ARMC | Training | pending quotation . target to submit by this week | Sarah | Sarah | 2026-08-07 | In Progress | 50000 | 14 |  | qusyairi.zolkefle@gmail.com | 05/08/2026, 9:55:35 am | 05/08/2026, 9:56:45 am
BPM MINDEF | Training | AI Training for 30 pax(2 phase) TTT for 10 pax | Adilah | qusyairi.zolkefle@gmail.com | 2026-09-15 | Pending | 134990 | 15 |  | qusyairi.zolkefle@gmail.com | 04/08/2026, 10:34:36 am | 12/08/2026, 11:08:43 am
UIA | Training | Semiconductor Training 26-27 November for 30 pax | Adilah | Adilah | 2026-11-26 | In Progress | 9000 | 15 |  | qusyairi.zolkefle@gmail.com | 04/08/2026, 10:32:21 am | 04/08/2026, 10:32:21 am
Mimos-IVV for KDN | Training | Data Science Training - 3days - August/October | zalina | zalina |  | In Progress | 20000 | 15 |  | qusyairi.zolkefle@gmail.com | 04/08/2026, 10:29:44 am | 04/08/2026, 10:29:44 am
UTP | Training | Semiconductor Training | Adilah | Adilah | 2026-10-20 | In Progress | 16500 | 15 | 20-22 October. Training for 5 lecturers | qusyairi.zolkefle@gmail.com | 04/08/2026, 10:22:13 am | 12/08/2026, 9:53:20 am
JTM | Training | Need to follow-up with En Nabil from JTM. | Fuzy | fuziah.rahim@mimos.my |  | Done | 0 | 19 | JTM masih belum terima baki peruntukan drpd menteri kewangan (MoF), so latihan Fasa2 ditunda ke 17 Ogos 2026. Akan update dari masa ke semasa. Tq. [5/8/2026] team akan follow up with JTM on the remaining balance | muhdciin@gmail.com | 31/07/2026, 4:15:06 am | 18/08/2026, 2:59:39 pm
Public Training | Training | Training delivered on 20 and 21 July 2026 | Farrah | farrah.johar@mimos.my | 2026-07-21 | Done | 0 | 19 | 20-21 July - Public Training AI System Thinking - 8 pax attended from KETENGAH, PERNAS, MAIS | muhdciin@gmail.com | 31/07/2026, 4:09:18 am | 31/07/2026, 4:09:18 am
Institut Aminuddin Baki | Training | TTT training delivery from 27 July until 31 July 2026 | Farrah | farrah.johar@mimos.my | 2026-07-31 | Done | 0 | 19 | 27-31 July - TTT AI for Institut Aminuddin Baki - 15 pax attended | muhdciin@gmail.com | 31/07/2026, 4:05:46 am | 04/08/2026, 10:06:05 am
UZMA | Training | HRD grant application from Uzma approved -RM21,000 | Farrah | farrah.johar@mimos.my | 2026-08-05 | In Progress | 21000 | 19 | 28 July - HRD grant application from Uzma approved -RM21,000 | muhdciin@gmail.com | 31/07/2026, 4:02:14 am | 04/08/2026, 10:07:37 am
TNB ILSAS | Training | Received LoA from TNB ILSAS for AI Training - RM82,000 | Farrah | farrah.johar@mimos.my |  | In Progress | 82000 | 19 | 28 July - Received LoA from TNB ILSAS for AI Training - RM82,000 - HRD grant application from Uzma approved -RM21,000 | muhdciin@gmail.com | 31/07/2026, 4:01:27 am | 31/07/2026, 4:09:40 am
INTAN | Training | - INTAN requested training outline for TTT & date for syllabus discussion - Start with one TTT class by Sept/Oct | Farrah | farrah.johar@mimos.my |  | In Progress | 0 | 19 | 24 July - Meeting with INTAN on CoE AI - They plan to have a 5-year plan for INTAN to develop CoE on AI and assign one AI Champion as trainer | muhdciin@gmail.com | 31/07/2026, 3:56:52 am | 31/07/2026, 4:09:49 am
Mimos-ISTIC INTERNATIONAL WORKSHOP ON QUANTUM INTELLIGENT 2026 | Workshop | Pending confirmation from Dr nordin and the team. program 29 sept-1october at mimos | zalina | zalina | 2026-07-31 | Pending | 0 | 22 | will have a follow up discussion later. | qusyairi.zolkefle@gmail.com | 28/07/2026, 10:41:53 am | 04/08/2026, 10:09:30 am
Company establishment process | General | 1)open account bank-document has been collected by bank.pending due to ssm ofline 2)loa to email by today 5/8/2026 3)email appoinment as commitee member(MAMC)-received nomination representative, to prepare letter. 4)request appointment letter from HR after received board MOM- pending from HR 5)company constitution - To review and submit to legal | sarah | sarah | 2026-08-28 | In Progress | 0 | 22 |  | qusyairi.zolkefle@gmail.com | 28/07/2026, 10:39:10 am | 05/08/2026, 10:01:36 am
mimos solutions workshop for MINDEF | Workshop | proposal and quotation has been submited to Mimos solutions. location at fairview hotel | zalina | zalina | 2026-09-02 | In Progress | 496800 | 22 |  | qusyairi.zolkefle@gmail.com | 28/07/2026, 10:32:44 am | 28/07/2026, 10:32:44 am
Protege Program under MTVET | Placement | join launching program, data to be confirm. Identified 20 protege placement within mimos group and subsidiary pending assessment / interview - will be commenced after launching date. | Sarah | sarah | 2026-08-14 | Pending | 720000 | 22 | plan to start by august | qusyairi.zolkefle@gmail.com | 28/07/2026, 10:26:30 am | 05/08/2026, 10:05:15 am
Nice Event at KLCC | Event | 26-28 August for MA at KLCC. Preparation using our own budget | Qusyairi/Omar | Qusyairi/Omar | 2026-08-26 | In Progress | 0 | 22 | [6/8/2026] now preparing the poster . need to prepare website before event. Training content need to update before the event day. | qusyairi.zolkefle@gmail.com | 28/07/2026, 10:22:38 am | 06/08/2026, 9:51:05 am
MIMOS IPM (for KDN Project) | Training | Proposals submitted to IPM (13 July, 15 July) 1. PMI-ACP Training (RM50,680) 2. Agile PM Essentials (RM18,240) | Zalina Sayuti | zalina@mimos.my | 2026-08-11 | Done | 68920 | 34 | Cost include exam fee & hotel/venue , zenith hotel. [6/8/2026] no respond from team. training cancel | zalinasayuti01@gmail.com | 16/07/2026, 9:51:51 am | 06/08/2026, 9:45:40 am
MIMOS ACADEMY Promoting and BD matters | Training | -TTT, Data scientist, Ai system thinking -Bulan 8,9,10,11 -socmed update everyday -sneak peek atau moment post training/pretraining -active kan socmed -data analytics (july) - to confirm PIC | Fatin Firzana binti Abdul Pata, Saidatul Farrah, Interns | firzana.pata@gmail.com |  | KIV | 0 | 34 |  | firzana.pata@gmail.com | 16/07/2026, 9:27:17 am | 12/08/2026, 10:17:01 am
2 HOUR TEASER Dr Hardy | Workshop | 1. Promote Dr Hardy's 2-hour workshop on socmed (malia to assist) 2. Malai to assist in CTA or copywriting | Fatin Firzana binti Abdul Pata | firzana.pata@gmail.com | 2026-07-30 | Done | 0 | 34 | Poster, dates, zoom link has been decided, to finalized before blasting | firzana.pata@gmail.com | 16/07/2026, 9:15:30 am | 04/08/2026, 10:17:04 am
training 20-21 july promoting | Training | 1. Promote 20-21 july public training 2. Update on trainee | Fatin Firzana binti Abdul Pata | firzana.pata@gmail.com |  | Done | 0 | 34 | refreshment class- 8 students | firzana.pata@gmail.com | 16/07/2026, 9:12:20 am | 28/07/2026, 9:57:56 am
BOD MEETING checklist | Meeting | 1. Attendance, email cosec to change venue 2. Check in registration and email bentara and receptionist 3. FnB for 11 pax 4. Mi - Latte - for appliances in round room 5. Mineral water | Fatin Firzana binti Abdul Pata | firzana.pata@gmail.com |  | Done | 0 | 34 |  | firzana.pata@gmail.com | 16/07/2026, 9:11:06 am | 28/07/2026, 9:58:23 am
KDN JPN - MyKAD Security Modernisation | Consulting | Phase 1 - 400k/4weeks | Omar Khalid | omarkhalidazmi@gmail.com | 2026-06-15 | Done | 0 | 35 |  | omarkhalidazmi@gmail.com | 15/07/2026, 2:34:00 pm | 06/08/2026, 2:49:32 pm
APD K-Youth Programme (Student University) | Training | online webinar for student university 238 pax x 4 cohorts 17 september onwards for first cohort. 2nd cohort 24 september | Adilah | adilah.nisman@mimos.my | 2026-09-17 | In Progress | 47600 | 36 | Kick off 1st cohort 17 Sept | firzana.pata@gmail.com | 14/07/2026, 11:00:47 am | 12/08/2026, 11:05:02 am
Hybrid Intelligence | Training | Get updates on PO - to purchase laptop & tablet - get quotation from MIMOS Solutions | Farrah | sayeedafarrah@gmail.com | 2026-07-09 | In Progress | 340000 | 47 |  | sayeedafarrah@gmail.com | 03/07/2026, 5:08:05 pm | 03/07/2026, 5:08:05 pm
GEA IPC | Training and Certication | Domentation and information on Equipment | Sarah Ramli | ssarah.ramli@gmail.com | 2026-07-10 | Pending | 3000000 | 47 | put on hold untill we have our own account. dr nizar need to go for training . need extra cost . | ssarah.ramli@gmail.com | 03/07/2026, 2:03:23 pm | 28/07/2026, 10:00:58 am
MASTIC (MOSTI) | Space Rental at MIMOS KHTP | The quotation and cost sheet have been sent to Mr. Fairus for approval. pending feedback from MASTIC | Abu Sa'id | saidrazak88@gmail.com | 2026-08-28 | Done | 8000 | 54 | MASTIC event: Roundtable discussion with industry (October 2026) | saidrazak88@gmail.com | 26/06/2026, 10:14:31 am | 18/08/2026, 5:16:53 pm
Unit Perancang Ekonomi Negeri (UPEN) Selangor | Training | -Submitted quotation -To follow up on the status of the proposal | Farrah | farrah.johar@mimos.my | 2026-06-30 | In Progress | 300000 | 55 |  | sayeedafarrah@gmail.com | 25/06/2026, 6:19:40 am | 25/06/2026, 6:19:58 am
Institut Aminuddin Baki | TTT and LLM Development | -Confirm with vendor for accommodation & training centre/venue -Send quotation to IAB | Farrah | farrah.johar@mimos.my | 2026-06-29 | In Progress | 49000 | 55 |  | sayeedafarrah@gmail.com | 25/06/2026, 6:12:54 am | 25/06/2026, 6:12:54 am
KPDN | Coordination of AI Vibe Coding | -Request status of ePerolehan for PO -Coordinate training (F&B) -Provide company documents to KPDN | Farrah | farrah.johar@mimos.my | 2026-06-30 | In Progress | 49500 | 55 |  | sayeedafarrah@gmail.com | 25/06/2026, 6:11:11 am | 25/06/2026, 6:11:11 am
Majlis TVET Negara | Perlaksanaan program TVET Frontier fellowship | to send and information to TVET based on email sent on 18th june 2026 | fuzi | fuzi | 2026-06-25 | In Progress | 10000 | 61 | [19/06/2026] 25 X 10,000 = 250,000. Artificial intelligent professional certification type of training still on discussion- Fresh Graduate | qusyairi.zolkefle@gmail.com | 19/06/2026, 10:07:18 am | 19/06/2026, 10:12:15 am
PKB | Training | 1. Nama pensijilan. 2. Badan yang mengeluarkan pensijilan. 3. Tahap pensijilan (Foundation, Professional, Expert dan sebagainya). 4. Tempoh dan kaedah peperiksaan. 5. Anggaran kos. 6. Pengiktirafan industri dan nilai tambah kepada organisasi. | Farrah | Farrah | 2026-06-19 | Pending | 0 | 65 |  | qusyairi.zolkefle@gmail.com | 14/06/2026, 10:14:51 pm | 14/06/2026, 10:15:39 pm
APD K-Youth Programme (Graduate) | Training Semiconductor | Training to be conducted from 1 September onwards 25 pax x 13 cohorts | Adilah | adilah | 2026-09-01 | In Progress | 455000 | 68 | 1st cohort to kick off 1 Sept | qusyairi.zolkefle@gmail.com | 12/06/2026, 4:20:38 pm | 12/08/2026, 11:05:29 am
EFC-K-Youth Programme (Graduate) | Training Semiconductor | Training to be conducted in Aug 20 pax x 1 cohort Selection process still on-going to find replacement for candidates who reject the offer | Adilah | adilah | 2026-08-17 | In Progress | 100000 | 68 | Kick off programme 17 Aug till 18 Sept | qusyairi.zolkefle@gmail.com | 12/06/2026, 4:18:54 pm | 12/08/2026, 11:05:46 am
Yayasan Peneraju-kredenzaa | Collaborator | NDA(send for stamping) and Teaming Agreement | Sarah | Sarah | 2026-07-31 | Done | 0 | 70 | [10/06/2026] NDA pending at legal for stamping [19/06/2026] Teaming agreement is on progress (direct nego) need to complete before august [28/07/2026] draft agreeement completed. already sent to kredenzaa for review [5/8/2026] teaming agreement completed to be sign by today. | qusyairi.zolkefle@gmail.com | 10/06/2026, 10:41:06 am | 05/08/2026, 10:06:33 am
MOSTI - Puan Sharifah Hafizah Hafizah | KHTP Space rental | Respond and prepare a quotation. | Abu Sa'id | saidrazak88@gmail.com | 2026-06-10 | Done | 0 | 70 | 19/06/2026 follow up offiline | saidrazak88@gmail.com | 10/06/2026, 10:22:00 am | 18/08/2026, 5:16:59 pm
Yayasan Peneraju | Training | To confirm on the site visit date 23rd june 2026 | fatin | fatin | 2026-06-23 | Done | 0 | 70 | [19/06/2026] 23rd june visit date , contact semi conductor pic. bring site visit JMTI | qusyairi.zolkefle@gmail.com | 10/06/2026, 9:55:39 am | 19/06/2026, 9:50:58 am
MPC | Training | to schedule a meeting with sally from MPC next week | firzana | firzana | 2026-06-26 | KIV | 0 | 70 | [10/06/2026] discuss on the price Additional training RFI [19/06/2026] postpone to another date [12/08/2026] no feedback from team | qusyairi.zolkefle@gmail.com | 10/06/2026, 9:41:15 am | 12/08/2026, 10:17:56 am
HRDC TP Registration | Training | Submit online form to become HRDC Training Provider | Ainur Najwa | ainurnajwa466@gmail.com | 2026-06-24 | KIV | 0 | 70 | [10/06/2026] Collect Document to submit online SSM form- Pending Trainer CV, TTT- Done To Submit MSA form . We need to prepare the MOA Integrity Pledge- Need to be signed by Ir. Dr. Nizar check on surat sewa and pemilikan bangunan [19/06/2026] pending SSM | ainurnajwa466@gmail.com | 10/06/2026, 9:26:56 am | 07/08/2026, 12:26:38 pm
MPC | Training | Need to prepare the quotation for Training rm19500 | farrah | farrah | 2026-06-12 | Done | 0 | 72 | [10/06/2026] Done | qusyairi.zolkefle@gmail.com | 08/06/2026, 12:16:56 pm | 10/06/2026, 10:15:39 am
APEC | Consulting | To assess 13 research paper registration and discuss with appointed contractor | Sarah Ramli | ssarah.ramli@gmail.com | 2026-08-28 | In Progress | 0 | 76 | [10/06/2026] dh discuss with contractor. 8 paper has been selected. next meeting will be on 16/6/2026 with contractor (um) briefing with paper authors 16/06/2026 [05/08/2026] handover engagement part with author to contractor(UM) however pending TOR from APEC. follow up has been made twice. | ssarah.ramli@gmail.com | 04/06/2026, 5:24:50 pm | 05/08/2026, 10:08:53 am
Checklist SST JMTI and SST Acceptance | Training | SST Signed by Acting CEO MSSB, witnessed by Pesuruhjaya Sumpah and send to JMTI (softcopy) due date is 04 June 2026 | Sarah Ramli | ssarah.ramli@gmail.com |  | Done | 0 | 76 |  | ssarah.ramli@gmail.com | 04/06/2026, 5:20:21 pm | 04/06/2026, 5:25:47 pm
APEC | APEC - Preparation and submission of paper | Finalise paper submission and provide a summary of the received papers’ status | Abu Sa'id | saidrazak88@gmail.com | 2026-06-05 | Done | 0 | 76 |  | saidrazak88@gmail.com | 04/06/2026, 9:48:12 am | 18/08/2026, 5:17:15 pm
Sempadan Teras Sdn Bhd | Corporate Shirt for MA teams | Raise PR and the purchase process | Abu Sa'id | saidrazak88@gmail.com | 2026-06-03 | Done | 0 | 76 |  | saidrazak88@gmail.com | 04/06/2026, 9:43:05 am | 18/08/2026, 4:17:20 pm
Bubblegift - ALTIX GROUP SDN BHD | MA Sourvenir | Need to raise PR CRYSTAL PLAQUE – CP377 33pcs | Ainur Najwa | ainurnajwa466@gmail.com | 2026-06-23 | Done | 0 | 76 | PR Approved, PO will sent by Procurement Need to finalize design [19/06/2026] po received. now pending item to be deliver [26/6/26] item delivered,pending payment (po,do,invoice,quotation need to be signed) | ainurnajwa466@gmail.com | 04/06/2026, 9:35:53 am | 07/08/2026, 12:23:36 pm
WICE Solution | Space Rental | Follow-up payment from WICE | Abu Sa'id | saidrazak88@gmail.com |  | Done | 0 | 92 | completed.payment slip has been forward to finance team | saidrazak88@gmail.com | 19/05/2026, 9:59:58 am | 04/06/2026, 9:50:50 am
Minister of Education, MOE | Space rental and food arrangement | 1. Prepare the space for a round table meeting room and technical setup, including tables and chairs. 2. Arrange equipment rental and catering orders. | Abu Sa'id | saidrazak88@gmail.com |  | Done | 0 | 92 |  | saidrazak88@gmail.com | 19/05/2026, 9:56:53 am | 04/06/2026, 9:50:59 am
Apec | Training | Revised ToR of the Researcher | Sarah Ramli | sarah | 2026-05-18 | Done | 0 | 97 |  | qusyairi.zolkefle@gmail.com | 14/05/2026, 2:36:30 pm | 04/06/2026, 5:17:06 pm
Aswara | Training | Adilah to assist provide the proposal and quotation | Omar khalid,Adila | Omar | 2026-06-19 | In Progress | 0 | 97 | [10/06/2026] proposal has been sent but yet to get the confirmation from Aswara [19/06/2026] proposal in progress [28/07/2026] proposal has been submited . pending from aswara | qusyairi.zolkefle@gmail.com | 14/05/2026, 11:31:05 am | 28/07/2026, 10:06:09 am
Air Borneo | Training | submitted quotation and proposal . now waiting for the feedback | Omar Khalid |  | 2026-06-26 | In Progress | 0 | 97 | meeting with air borneo next wednesday -lcct [19/06/2026] pending techincal online meeting. to discuss on the scope [6/08/2026] pending training date to be provide | qusyairi.zolkefle@gmail.com | 14/05/2026, 11:29:44 am | 06/08/2026, 2:52:30 pm
National AI Office | Training | waiting for tender to be out | Adilah | Adilah | 2026-06-19 | In Progress | 0 | 97 | Adilah to assist preparing the Technical Documents [4/06/2026] proposal ,cost shit and presention to msmc target to be ready by this week | qusyairi.zolkefle@gmail.com | 14/05/2026, 11:27:39 am | 10/06/2026, 11:07:46 am
INSKEN | Training | confirmed 9 and 10 june for in house training in mimos. po will be submited by next week | Omar Khalid | omar | 2026-06-09 | Done | 0 | 97 | [4/6/2026] today decide which hotel to proceed - cost will be pay by mimos - survey 3 hotel and do some rating . check wifie , aircond and environment [19/06/2026] pending invoice from finance. need to register insken [06/08/2026] pending for 2nd batch training | qusyairi.zolkefle@gmail.com | 14/05/2026, 11:25:53 am | 06/08/2026, 2:55:18 pm
TalentCorp | Consulting | Arrange meeting with madhavan.balan@talentcorp.com.my to meet the CEO | Fatin Firzana | fatin.pata@mimos.my | 2026-05-15 | Done | 0 | 97 | date still in discussion [4/6/2026] discussion 12/6/2026 9.30 am suhairi,sarah,farah,qusyairi and dr nizar | qusyairi.zolkefle@gmail.com | 14/05/2026, 10:04:41 am | 13/06/2026, 12:21:31 am
Ekuinas | Consulting | adila quotation and proposal, ai system thinking + inhouse TTT | Adila | adilah.nisman@mimos.my | 2026-06-19 | In Progress | 0 | 97 | [10/06/2026] Proposal and quoatation has been sent. stil yet to get the confirmation from Ekuinas | qusyairi.zolkefle@gmail.com | 14/05/2026, 9:57:47 am | 12/08/2026, 11:09:53 am
Glamprint | Raise PR | Raise PR for MA goodies and sourvenir | Ainur Najwa | ainurnajwa466@gmail.com | 2026-06-10 | Done | 0 | 98 | PRINTED MUG & PRINTING SERVICE FOR PAPER BAG PR approved, PO will sent by Procurement next step, DO and invoice as item is currently in making [19/06/2026] item received. pending sign off from en fairuz and send to finance team | ainurnajwa466@gmail.com | 13/05/2026, 11:30:52 am | 07/08/2026, 12:26:22 pm
Daffodil | Training | Proposal for Daffodil International University | Ainur Najwa | ainurnajwa466@gmail.com | 2026-05-18 | Done | 0 | 98 | 3 Proposal 5 Days Online for Lecturer 10 Days Hybrid for Lecturer 5 Days Hybrid for Student [4/06/2026] completed. pending fuzi to review | ainurnajwa466@gmail.com | 13/05/2026, 11:25:20 am | 04/06/2026, 9:42:00 am
MARA | Consulting | Discussion with KP MARA | Fatin Firzana | fatin.pata@mimos.my | 2026-09-11 | In Progress | 0 | 98 | Postponed to 11th September evening, will update more after confirmation.meeting with penolong KP | qusyairi.zolkefle@gmail.com | 13/05/2026, 10:32:54 am | 18/08/2026, 9:45:18 am
JTM | Consulting | Firzana, need to schedule a meeting with PA datuk Rospiagos, CEO JTM by next week. | Fatin Firzana | fatin.pata@mimos.my | 2026-05-18 | Done | 0 | 98 | completed. | qusyairi.zolkefle@gmail.com | 13/05/2026, 10:30:17 am | 26/05/2026, 9:43:10 am
Mimos Berhad | Consulting | Contact JT for agreement mimos and ma untuk project mgmt services commission | Muhammad Qusyairi Zolkefle | qusyairi.zolkefle@gmail.com | 2026-08-28 | In Progress | 0 | 98 | plan to do MSA with Mimos Holding | qusyairi.zolkefle@gmail.com | 13/05/2026, 9:56:33 am | 05/08/2026, 9:49:33 am
Smart Sabah | Training | Farrah to follow up on the status with Smart Sabah | Farrah | farrah.johar@mimos.my | 2026-06-12 | In Progress | 0 | 98 | [10/06/2026] still on discussion. Planning to have training at penang. | qusyairi.zolkefle@gmail.com | 13/05/2026, 9:53:24 am | 10/06/2026, 10:47:20 am
Tanzania MOF | Training | Tanzania MOF audit team wants to come to Malaysia Aug 10 for 2 weeks for Audit using AI and Risk . Adila to proceed with quotation and proposal | Qusyairi/Adila | Qusyairi | 2026-08-17 | Pending | 0 | 98 | [10/06/2026] Adila will have separate discussion with dr nizar [12/8/2026] preparing proposal 2 program. Risk management (2days) and audit. uproft payment 100%. risk management 2 days rm 30k Audit 2 weeks RM 100k convert in USD [12/8/2026] pending gov fund from tanzania. then they will inform us [17/08/2026] Proposal submitted. now pending feedback from tanzania team | qusyairi.zolkefle@gmail.com | 13/05/2026, 9:46:04 am | 17/08/2026, 12:03:52 pm
Institute Pendidikan Guru | Consulting | Omar/Nizar to contact Institute Pendidikan Guru HQ Dr zanariah, timbalan reactor 016-3404380 | Omar | Omar | 2026-06-12 | In Progress | 0 | 98 | [10/06/2026] contact ipg for further discussion | qusyairi.zolkefle@gmail.com | 13/05/2026, 9:38:32 am | 12/08/2026, 11:07:59 am
yayasan sarawak | Training | Omar to visit Yayasan Sarawak | Omar Khalid | omar.azmi@mimos.my | 2026-06-30 | KIV | 0 | 98 | omar just get the person in charge. will communicate for futher discussion [19/06/2026] no update from Yayasan Sarawak | qusyairi.zolkefle@gmail.com | 13/05/2026, 9:32:08 am | 06/08/2026, 2:53:07 pm
UKM Pakarunding | Training | To confirm on the second meeting with dean UKM and NDA | Qusyairi | qusyairi.zolkefle@mimos.my | 2026-06-12 | KIV | 0 | 104 | To confirm second meeting with Dean of UKM set meeting with intan NDA | firzana.pata@gmail.com | 07/05/2026, 4:24:04 pm | 18/08/2026, 2:58:07 pm
UKM Pakarunding | Training | ESG Program affiliate with UKM. RBD roles as Training Provider (TP) | Qusyairi | qusyairi.zolkefle@mimos.my | 2026-06-12 | KIV | 0 | 104 | [10/06/2026] passed NDA to UKM and RBD using MSSB template | firzana.pata@gmail.com | 07/05/2026, 4:15:31 pm | 18/08/2026, 2:57:58 pm
Mimos Academy | Development | Website MIMOS Academy to deploy | Suhairi Soobni | suhairi.soobni@mimos.my | 2026-06-30 | Done | 0 | 105 | [10/06/2026] All internship staff need to assist on the development solihin will be admin for this system | firzana.pata@gmail.com | 06/05/2026, 2:54:03 am | 11/08/2026, 2:32:14 pm
APEC | Training | The Terms of Reference (ToR) has been submitted for review. The venue hosting site survey is pending. The researcher for the paper is yet to be identified. | Sarah Ramli | sitisarah.ramli@mimos.my | 2026-05-15 | Done | 0 | 105 |  | firzana.pata@gmail.com | 06/05/2026, 2:52:57 am | 04/06/2026, 5:17:31 pm
- | Governance | Probation Suhairi and renewal | Sarah Ramli | sitisarah.ramli@mimos.my | 2026-05-07 | Done | 0 | 105 |  | firzana.pata@gmail.com | 06/05/2026, 2:50:50 am | 04/06/2026, 5:17:40 pm
- | Development | Settle the domain and hosting | Abu Sa'id | abu.razak@mimos.my | 2026-05-08 | Done | 0 | 105 |  | firzana.pata@gmail.com | 06/05/2026, 2:49:40 am | 18/05/2026, 2:47:45 pm
MCMC | Training | Proposal submission | Farrah/Omar | Farrah/Omar | 2026-05-18 | Done | 21000 | 106 | submited 1 quotation last friday by omar grayce(hr director) | firzana.pata@gmail.com | 05/05/2026, 2:56:58 pm | 19/08/2026, 10:01:58 am
Bank Rakyat | Development | Bank Rakyat proposal | Omar Khalid | omar.azmi@mimos.my | 2026-06-19 | KIV | 0 | 106 | Submitted all pending docs 2 weeks ago. Now Awaiting response from Bank Rakyat [14-05-2026] need to submit proposal to dr Nazrul and VP Mr.fendy. [19/06/2026] pending vendor registration [06/08/2026] pending feedback from bank rakyat | firzana.pata@gmail.com | 05/05/2026, 2:56:04 pm | 12/08/2026, 4:27:53 pm
- | Development | Guarantee Letter- KRIMS Venture | Sarah Ramli | sitisarah.ramli@mimos.my | 2026-05-08 | Done | 0 | 106 |  | firzana.pata@gmail.com | 05/05/2026, 2:55:05 pm | 04/06/2026, 5:17:49 pm
ET TAN | Development | Communicate 10k | Zalina Sayuti | zalina.sayuti@mimos.my | 2026-05-08 | Done | 0 | 106 |  | firzana.pata@gmail.com | 05/05/2026, 2:53:45 pm | 06/08/2026, 9:41:33 am
EMSpiral PLT | Training | Follow up Mr Elangeshwaran | Omar Khalid | omar.azmi@mimos.my | 2026-06-19 | Done | 0 | 107 | They just signed the NDA yesterday. [14-05-2026] waiting for other documents to be submit [19/06/2026] nda sign off completed | firzana.pata@gmail.com | 04/05/2026, 3:48:54 pm | 19/06/2026, 10:19:57 am
MRSM | Training | Omar send proposal for AI for MRSM throughout Malaysia. 5 Days. | Omar Khalid | omar.azmi@mimos.my | 2026-05-18 | Done | 0 | 107 | Submitted the sylibus for MRSM. Price will discuss for MRSM special rate [14-05-2026] still waiting for the price from DR [19/06/2026] no response from MRSM | firzana.pata@gmail.com | 04/05/2026, 3:47:11 pm | 15/07/2026, 3:00:22 pm
- | Development | Posting for MARA TVET Expo | Sholihin | sholihin.abdullah@mimos.my | 2026-05-04 | Done | 0 | 107 |  | firzana.pata@gmail.com | 04/05/2026, 3:45:06 pm | 13/05/2026, 11:17:40 am
- | Development | Raise PR for MIMOS Academy goodies | Fatin Firzana | fatin.pata@mimos.my | 2026-05-08 | Done | 0 | 107 | Ainur will be the pic for this task. | firzana.pata@gmail.com | 04/05/2026, 2:32:49 pm | 11/08/2026, 2:31:40 pm
SIRIM | Training | Contact SIRIM Academy | Zalina Sayuti | zalina@mimos.my | 2026-06-12 | Done | 0 | 107 | 10/06/2026 NDA has been sent to SIRIM. Pending hardcopy from SIRIM Academy 6/8/2026 NDA completed | firzana.pata@gmail.com | 04/05/2026, 2:19:30 pm | 06/08/2026, 9:41:10 am
Public | Training | Create Eventbrite and promote to past participants or the public | Abu Sa'id | abu.razak@mimos.my | 2026-05-06 | Done | 0 | 107 |  | firzana.pata@gmail.com | 04/05/2026, 2:17:58 pm | 08/05/2026, 6:11:44 pm
KVeSB & Mimos holding sdn bhd | Shareholder Agreement | JVA and IP | Siti Sarah | sitisarah.ramli@mimos.my | 2026-06-12 | Done | 0 | 107 | [10/06/2026] JVA Target to be sign this week Target Register SSM next week ip due diligences has been submitted to legal [5/08/2026] JVA executed and sign 18 Jun 2026 | firzana.pata@gmail.com | 04/05/2026, 2:03:37 pm | 05/08/2026, 9:50:26 am
MBOT | Training | MBOT accreditation program | yusof | yusof | 2026-08-21 | Done | 0 | 107 | [10/06/2026] 1)documents readiness in progress 2)memo to request fund from mssb 3)collect internal documents and verfify from dr Afiq [12/8/2026] proceed with payment.yusuf will follow up with Mbot officer | firzana.pata@gmail.com | 04/05/2026, 8:33:49 am | 18/08/2026, 2:57:14 pm
Sirim | Training | To Send ISO14000 Proposal and Quotation | Fuzi | ahnizar@gmail.com | 2026-05-05 | Done | 0 | 110 | SIRIM is taking time to provide the course outline, and the industry has opted to proceed with another TP in the meantime. | ahnizar@gmail.com | 01/05/2026, 5:02:42 pm | 14/05/2026, 5:15:07 pm